## Milestones
PROJECT MILESTONES
| Month | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
1 | Conduct the survey | bar: Jan 1 to Apr 14
Survey design | bar: Jan 1 to Jan 2
Pilot survey for focused group | bar: Jan 3 to Feb 5
Conduct the survey | bar: Feb 6 to Apr 14
2 | Write up the results of the survey | bar: Apr 15 to Jun 22
Initial analysis of results | bar: Apr 15 to May 18
Draw conclusion to adjust the syllabus | bar: May 19 to Jun 22
3 | Develop Python coding materials | bar: May 19 to Sep 36
Basic Python + libraries | bar: May 19 to Jun 22
Automate emails + texts | bar: Jun 23 to Jun 24
API calls for financial statement analysis | bar: Jul 25 to Jul 26
Event study | bar: Jul 27 to Jul 28
Textual analysis | bar: Aug 29 to Aug 30
HTML/CSS | bar: Aug 31 to Aug 32
Web scrapping | bar: Sep 33 to Sep 34
Machine learning | bar: Sep 35 to Sep 36
4 | Write up academic articles | bar: Aug 29 to Dec 48
Paper 1 | bar: Aug 29 to Oct 38
Paper 2 | bar: Oct 39 to Dec 48
5 | Report research findings and education materials to the CPAA and submit papers to journals